## Gantt Chart
Corrective action plan for soft spool spool M4 sample with chamfer and center hole angle deviation |  |  | 41456 | 41471 |  | CAR-13001
Enter Project Range
|  |  | Start Date | End Date
|  |  | 41456 | 41471
|  |  | Zoom (enter 1 for Daily, 7 for Weekly)---> | 1 | Work estimated |  |  | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3
| Phase / Task | Person Responsible | Start Date | End Date | % Complete | Work done | Work Left | 41456 | 41457 | 41458 | 41459 | 41460 | 41461 | 41462 | 41463 | 41464 | 41465 | 41466 | 41467 | 41468 | 41469 | 41470 | 41471
Spool 700.001-F347555.01-0021 |  |  | 41456 | 41471 |  |  | 16
Turning(with differ chamfers and new center hole drill) |  | Michael Meyer | 41456 | 41458 |  |  | 3
QA measuring |  | Steve.Feng | 41459 | 41460 | 100 | 2 | 0
Sand blasting | 卡Medium心内部Requirements讨论 | Michael Meyer | 41463 | 41463 | 100 | 1 | 0
Grinding and brushing | 卡Medium心技术Requirements签批 | Michael Meyer | 41464 | 41465 | 100 | 2 | 0
QA Measuring | 科技部出可研Report | Steve.Feng | 41466 | 41467 | 100 | 2 | 0
Prepare report | 系统卡发Initiation | Steve.Feng | 41470 | 41471 | 100 | 2 | 0
The sand blasting machine was disassemblied and will be here within three months.So this project starts from 1st.July.2013 ,the center hole drill for 120°±10° will be arrive before the sand blasting machine. | [7 empty] | 2: Update date:2013/03/28
Note on D4: If wanted, enter the start date for the scale of the gantt chart. If none is provided, the configuration will be done automatically starting from the date of earliest start date.

## Gantt Chart (2)
Corrective action plan for soft spool M4 sample devication |  |  | 41456 | 41470 |  | CAR-13001
Enter Project Range
|  |  | Start Date | End Date
|  |  | 41456 | 41470
|  |  | Zoom (enter 1 for Daily, 7 for Weekly)---> | 1 |  |  |  | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2
| Phase / Task | Person Responsible | Start Date | End Date | % Complete | Work done | Duration days | 41456 | 41457 | 41458 | 41459 | 41460 | 41461 | 41462 | 41463 | 41464 | 41465 | 41466 | 41467 | 41468 | 41469 | 41470
Spool 700.002-F347558-0021 |  |  | 41456 | 41470 |  |  | 15
Turning(with different chamfers and new center hole drill) |  | Michael Meyer | 41456 | 41458 |  |  | 3
QA measuring |  | Steve.Feng | 41459 | 41460 | 100 | 2 | 2
Sand blasting | 卡Medium心内部Requirements讨论 | Michael Meyer | 41463 | 41463 | 100 | 1 | 1
Grinding and brushing | 卡Medium心技术Requirements签批 | Michael Meyer | 41464 | 41465 | 100 | 2 | 2
QA Measuring | 科技部出可研Report | Steve.Feng | 41466 | 41467 | 100 | 2 | 2
Prepare report | 系统卡发Initiation | Steve.Feng | 41470 | 41470 | 100 | 1 | 1
The sand blasting machine was disassemblied and will be here within three months.So this project starts from 1st.July.2013 ,the center hole drill for 120°±10° will be arrive before the sand blasting machine. | [7 empty] | 2: Update date:2013/03/28
Note on D4: If wanted, enter the start date for the scale of the gantt chart. If none is provided, the configuration will be done automatically starting from the date of earliest start date.