## GanttChart
[Project Name] Project Schedule
[Company Name]
| Project Lead: |  |  | [ John Doe ]
| Project Start Date: |  |  | 2020-03-23 | time axis 2020-03-23 to 2020-05-17
| Display Week: |  |  | 1 |  |  |  |  | 2020-03-23: Week 1; 2020-03-30: Week 2; 2020-04-06: Week 3; 2020-04-13: Week 4; 2020-04-20: Week 5; 2020-04-27: Week 6; 2020-05-04: Week 7; 2020-05-11: Week 8
[9 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | [Task Category] | [Name]
1.1 | [Task] | [Name] |  | 2020-03-23 | 2020-03-28 | 6 | 100% | 5
1.2 | [Task] |  |  | 2020-03-29 | 2020-04-02 | 5 | 50% | 4
1.3 | [Task] |  |  | 2020-04-03 | 2020-04-06 | 4 | 75% | 2
1.4 | [Task] |  |  | 2020-03-25 | 2020-03-28 | 4 | 50% | 3
1.5 | [Task] |  |  | 2020-03-29 | 2020-03-30 | 2 | 50% | 1
1.6 | [Task] |  |  | 2020-03-24 | 2020-03-26 | 3 | 50% | 3
1.7 | [Task] |  |  | 2020-03-27 | 2020-03-31 | 5 | 50% | 3
1.8 | [Task] |  |  | 2020-04-01 | 2020-04-07 | 7 | 50% | 5
1.9 | [Insert Rows above this one, then Hide or Delete this row]
2 | [Task Category]
2.1 | [Task] |  |  | 2020-03-23 | 2020-03-23 | 1 | 0% | 1
2.2 | [Task] |  |  | 2020-03-24 | 2020-03-24 | 1 | 0% | 1
2.3 | [Task] |  |  | 2020-03-25 | 2020-03-25 | 1 | 0% | 1
2.4 | [Task] |  |  | 2020-03-26 | 2020-03-26 | 1 | 0% | 1
2.5 | [Insert Rows above this one, then Hide or Delete this row]
3 | [Task Category]
3.1 | [Task] |  |  | 2020-03-23 | 2020-03-23 | 1 | 0% | 1
3.2 | [Task] |  |  | 2020-03-24 | 2020-03-24 | 1 | 0% | 1
3.3 | [Task] |  |  | 2020-03-25 | 2020-03-25 | 1 | 0% | 1
3.4 | [Task] |  |  | 2020-03-26 | 2020-03-26 | 1 | 0% | 1
3.5 | [Insert Rows above this one, then Hide or Delete this row]
4 | [Task Category]
4.1 | [Task] |  |  | 2020-03-23 | 2020-03-23 | 1 | 0% | 1
4.2 | [Task] |  |  | 2020-03-24 | 2020-03-24 | 1 | 0% | 1
4.3 | [Task] |  |  | 2020-03-25 | 2020-03-25 | 1 | 0% | 1
4.4 | [Task] |  |  | 2020-03-26 | 2020-03-26 | 1 | 0% | 1
4.5 | [Insert Rows above this one, then Hide or Delete this row]
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
CATEGORY ROWS and WBS NUMBERING
1 | [ Task Category (label only) ]
1.1 | [ Level 2 Task ]
1.1.1 | . [ Level 3 Task ]
1.1.1.1 | . . [ Level 4 Task ]
Examples of ways to define the Start, End, and Duration of tasks
1 | [ Task Category (summary) ] |  |  | 2020-03-01 | 2020-03-01 | 1 |  | 0
2 | Milestone |  |  | 2020-03-01 | 2020-03-01
2.1 | [ Start Date and Calendar Days ] |  |  |  | 0 |  |  | 0
2.2 | [ Start Date and End Date ] |  |  |  |  | 0 |  | 0
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version includes template rows that allow you to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.